## Definitions
Risk Register — Definitions
Likelihood Levels
Level | Score | Description
Almost Certain | 5 | Expected to occur in most circumstances; has happened repeatedly in similar contexts.
Likely | 4 | Will probably occur; strong evidence or history of occurrence.
Possible | 3 | Could occur at some point; some evidence or precedent exists.
Unlikely | 2 | Not expected, but could occur under unusual circumstances.
Rare | 1 | May only occur in exceptional circumstances; very low probability.
Consequence Levels
Level | Score | Description
Catastrophic | 5 | Complete project failure, serious injury, or total loss of key deliverable.
Major | 4 | Significant impact on project objectives, timeline, or safety; major rework required.
Moderate | 3 | Noticeable impact; some rework, delay, or reduced quality, but recoverable.
Minor | 2 | Small impact easily addressed with minimal effort or cost.
Insignificant | 1 | Negligible impact; no meaningful effect on project outcomes.
Risk Score Calculation
Risk Score = Likelihood Score + Consequence Score
Risk Levels
Risk Level | Score Range | Interpretation
Low | 2 – 4 | Acceptable risk; manage through routine procedures.
Moderate | 5 – 6 | Monitor closely; implement mitigation measures where practical.
Significant | 7 | Requires active management and a documented mitigation plan.
High | 8 – 9 | Unacceptable without immediate mitigation; escalate to project lead.
Extreme | 10 | Critical risk; stop activity until risk is reduced or eliminated.
Key Terms
Term |  | Definition
Risk | An uncertain event or condition that, if it occurs, could have a positive or negative effect on one or more project objectives.
Likelihood | The probability of the risk event occurring, rated on a 5-point scale from Rare (1) to Almost Certain (5).
Consequence | The severity of impact if the risk event occurs, rated on a 5-point scale from Insignificant (1) to Catastrophic (5).
Risk Score | A numerical value calculated by adding the Likelihood score and the Consequence score (range: 2–10).
Risk Level | A qualitative classification (Low to Extreme) derived from the Risk Score.
Mitigation Measures | Actions planned or taken to reduce the likelihood or consequence of a risk.
Residual Risk | The remaining level of risk after mitigation measures have been applied.
Risk Area | The category to which the risk belongs (e.g., Mechanical, Electrical, Safety/WHS, Project Management).

## Risk Register
|  |  |  | Columns F, H, I, J auto populates |  |  |  |  | Be detailed in measures. Most areas will have 3 to 5 mitigations required. |  | Columns M,O,P, Q auto populates
Risk ID | Risk Area | Risk Description | Likelihood (Select from pull down) | Score | Consequence (Select from pull down) | Score | Risk Score | Level of Risk | Mitigation measures | RESIDUAL Likelihood (Select from pull down) | Score | RESIDUAL Consequence (Select from pull down) | Score | Risk Score | RESIDUAL Level of Risk
1 | Technical / Data | PNGworkforce blocks the scraper or changes its HTML structure mid-build, causing the scraper to fail silently and miss postings. | Likely | 4 | Moderate | 3 | 7 | Significant | Pick a low-friction source (PNGworkforce) where the existing Easy Skill prototype already proves scraping is viable. Implement graceful failure: log a warning, return empty list, continue pipeline on synthetic data only. Add a smoke test on saved HTML fixtures that catches schema changes within 24 hours. Maintain a fallback synthetic-only mode so demo and evaluation can run without live scraping. | Unlikely | 2 | Minor | 2 | 4 | Low
|  | Google Gemini API free-tier quota is exhausted partway through KPI evaluation runs, blocking measurement of classification accuracy. | Possible | 3 | Major | 4 | 7 | Significant | Set a hard run-cap of 5 evaluation passes across the 200-record dataset (~1,000 API calls total — well within free tier). Cache LLM responses locally during development so re-runs don't consume quota. Have an Anthropic API key as paid backup with A$50 spend cap configured before evaluation week. Run evaluation in off-peak hours to avoid rate-limit contention. | Unlikely | 2 | Minor | 2 | 4 | Low
|  | Synthetic dataset does not adequately represent real PNGworkforce posting variability, making the reported classification accuracy unrepresentative of production performance. | Likely | 4 | Moderate | 3 | 7 | Significant | Mix 120 real scraped postings with 80 hand-authored synthetic postings (60/40 split). Member 3 (Industry Analyst) curates edge cases: ambiguous role titles, watchlist aliases, bilingual postings. Document the dataset composition explicitly in §5.2 so markers and the future production team understand the ceiling. Report synthetic-only and real-data-included accuracy separately if they differ meaningfully. | Possible | 3 | Minor | 2 | 5 | Moderate
2 | Project Management | A team member is unavailable during the build sprints (W7–W10) due to competing academic workloads, illness, or personal commitments, delaying the PoC. | Possible | 3 | Major | 4 | 7 | Significant | RACI matrix in §2.3 ensures every deliverable has cross-cover identified up front. All code committed to shared GitHub from W1 so any member can pick up another's work within one day. Weekly sync with M1 chairing — blockers surfaced and reallocated within 24 hours. Sprint 1 contingency: if scope at risk, cut Slack delivery to console-only output, keep classification working. | Unlikely | 2 | Moderate | 3 | 5 | Moderate
|  | Scope creep — group attempts to build Mode Push or Mode Publish features beyond the agreed minimal Mode Monitor slice — leaving insufficient time for KPI evaluation and report writing. | Possible | 3 | Major | 4 | 7 | Significant | Lock scope in §1.3 of the report: PoC = Mode Monitor only; Mode Push and Mode Publish are designed but not built. M4 (Solutions Architect) and M5 (PoC Engineer) jointly guard scope at every weekly sync. W8 contingency switch: if Sprint 1 slips, cut PoC to scraper + BigQuery + CSV (drop the LLM agent). Report writing starts in parallel from W4, not deferred to after the build. | Unlikely | 2 | Moderate | 3 | 5 | Moderate
3 | Cybersecurity / Privacy | Real candidate or client PII from Easy Skill's HubSpot or Teamtailor is inadvertently used in PoC datasets, breaching Australian Privacy Act 1988 (Cth) and Australian Privacy Principles. | Unlikely | 2 | Catastrophic | 5 | 7 | Significant | Scope §1.3 explicitly excludes real PII; PoC uses synthetic data and publicly-scraped job postings only. All datasets reviewed by M3 before commit to ensure no PII inclusion. GitHub repository configured with secret-scanning enabled; .gitignore excludes data/ subfolder containing any candidate-resembling content. Cloud region for any future deployment locked to ap-southeast-2 (Sydney) for data sovereignty. | Rare | 1 | Major | 4 | 5 | Moderate
|  | API keys (Gemini, Slack webhook, future Anthropic) are accidentally committed to the GitHub repository, exposing credentials to public access. | Possible | 3 | Major | 4 | 7 | Significant | All secrets stored in .env file; .env added to .gitignore from W1 commit one. GitHub repository configured with push-protection and secret-scanning alerts. Provide a .env.example template in the repo so contributors know structure without exposing values. Use Gemini free-tier keys only during the PoC; rotate any key that lands in git history within 24 hours. | Unlikely | 2 | Moderate | 3 | 5 | Moderate
|  | Prompt injection in scraped job posting content manipulates the Signal Analyst agent's classification or extracts the system prompt, compromising the integrity of the digest. | Possible | 3 | Moderate | 3 | 6 | Moderate | Treat all scraped content as untrusted input — log raw content separately from LLM-processed output. Use structured output (Gemini JSON mode) so the LLM cannot return arbitrary instructions. Pre-filter raw content for suspicious patterns (e.g., 'ignore previous instructions') before LLM call. Document this as a known limitation in §5.2 lessons learned; flag full prompt-injection defence as a Phase 2 control. | Unlikely | 2 | Minor | 2 | 4 | Low
4 | Academic / Assessment | Use of Claude Code or other AI tools for PoC implementation is flagged as academic misconduct because the assessment brief states 'no AI tools permitted'. | Possible | 3 | Catastrophic | 5 | 8 | High | Confirm in writing with the unit coordinator before W1 whether AI-assisted coding (Claude Code, GitHub Copilot) is permitted for the PoC build (separate from report writing). Retain the coordinator's reply in the project records. If permitted, disclose AI assistance in both the README and §5.2: 'Code scaffolding was assisted by Claude Code; all architectural decisions, integration logic, and final review were authored by the project team.' All report prose authored by group members only — no AI assistance in writing. | Rare | 1 | Major | 4 | 5 | Moderate
|  | Turnitin similarity score for the report exceeds acceptable thresholds due to extensive direct quotation from the Easy Skill MIOS specification document or standards references. | Possible | 3 | Major | 4 | 7 | Significant | Paraphrase the MIOS specification rather than quoting directly; reserve direct quotes for definitions only (< 15 words each, max one per source). Run Turnitin pre-check at W11 before final submission to identify high-similarity passages. Use APA in-text citations for every reference to standards (NIST, ISO, OWASP) and vendor documentation. M5 owns the Turnitin pre-check and addresses any flagged passages with the group before W12 submission. | Unlikely | 2 | Moderate | 3 | 5 | Moderate
|  | Backup demo recording is missing or fails to play during the presentation, and the live demo also fails, resulting in loss of demonstration marks. | Possible | 3 | Moderate | 3 | 6 | Moderate | M5 records the full end-to-end demo by W11, before the presentation week. Test the recording on the presentation machine in advance; carry on USB plus cloud-link backup. Rehearse the live demo at least twice during W12, including the offline fallback path. Pre-stage the synthetic dataset and SQLite database so the demo runs even without internet. | Unlikely | 2 | Minor | 2 | 4 | Low
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
DO NOT COMPLETE MORE THAN 50 ROWS

## Risk Matrix
Risk Assessment Matrix
Risk Score = Likelihood + Consequence
CONSEQUENCE
|  | Insignificant (1) | Minor (2) | Moderate (3) | Major (4) | Catastrophic (5)
LIKELIHOOD | Almost Certain (5) | 6 Moderate | 7 Significant | 8 High | 9 High | 10 Extreme
| Likely (4) | 5 Moderate | 6 Moderate | 7 Significant | 8 High | 9 High
| Possible (3) | 4 Low | 5 Moderate | 6 Moderate | 7 Significant | 8 High
| Unlikely (2) | 3 Low | 4 Low | 5 Moderate | 6 Moderate | 7 Significant
| Rare (1) | 2 Low | 3 Low | 4 Low | 5 Moderate | 6 Moderate
Risk Level Legend
Low | Score: 2 – 4
Moderate | Score: 5 – 6
Significant | Score: 7
High | Score: 8 – 9
Extreme | Score: 10